## Website Migration Tracker
# | Page Name | URL | MD Filename / Action | Status | Page Description
1 | Home | https://fasttrackr.ai/ | pages/home.md | ✅ Complete | Main homepage covering product overview, Advisor Transitions, Client Onboarding, Document Intelligence, Meeting Assistant, integrations, testimonials, FAQs, and contact form.
2 | Podcast | https://fasttrackr.ai/podcast | pages/podcast.md | ✅ Complete | Landing page for the 'Advisor Ally' podcast. Includes description, artwork, and listen links for YouTube, Apple Podcasts, and Spotify.
3 | Contact | https://fasttrackr.ai/contact | pages/contact.md | ✅ Complete | Contact/inquiry page with a form (Name, Email, Topic, Message) and FAQ section. Set to noindex in meta.
4 | Terms of Service | https://fasttrackr.ai/tos | pages/terms-of-service.md | ✅ Complete | Full Terms of Service (last updated 18 Nov 2025). Covers definitions, service scope, fees, confidentiality, warranties, liability, data retention, IP ownership, and dispute resolution. Includes Document Processing Module terms.
5 | TOS — Advisor Transition Platform | https://fasttrackr.ai/tos-transitions | pages/tos-transitions.md | ✅ Complete | Separate TOS specifically for the FastTrackr Advisor Transition Platform (last updated 13 Apr 2026). Covers neutral platform role, broker protocol compliance, prohibited uses, data controller/processor relationship, and indemnification.
6 | Privacy Policy | https://fasttrackr.ai/privacy-policy | pages/privacy-policy.md | ✅ Complete | Full Privacy Policy (last updated 18 Nov 2025). Covers data collection (Personal, Meeting, Email, CRM, Document), retention schedules, security, third-party AI services, CRM integrations, client consent requirements for Document Processing Module, and user rights.
7 | Privacy Policy — Advisor Transitions | https://fasttrackr.ai/privacy-policy-transitions | pages/privacy-policy-transitions.md | ✅ Complete | Separate Privacy Policy for the FastTrackr Advisor Transition Platform (last updated 13 Apr 2026). Covers dual controller/processor role, Client Data uploaded by users (including SSNs), broker protocol responsibility, and data retention schedules for transition projects.
8 | Client Privacy Notice | https://fasttrackr.ai/client-privacy-notice | pages/client-privacy-notice.md | ✅ Complete | Plain-language privacy notice for end-clients (clients of advisors using FastTrackr Transition Platform). Explains what data is collected, who can see it, how it is protected, and client rights. ~2 min read.
9 | Client Data Consent & Acknowledgment | https://fasttrackr.ai/client-data-consent-acknowledgment | pages/client-data-consent-acknowledgment.md | ✅ Complete | Short plain-language consent document for clients accessing the FastTrackr portal during an advisor transition. Records checkbox consent with date/time, email, and IP. Pairs with the Client Privacy Notice.
10 | Zoom Help Documentation | https://fasttrackr.ai/zoom-help-documentation | pages/zoom-help-documentation.md | ✅ Complete | Help documentation for the Zoom / calendar integration. Covers installation (connect calendar), automatic meeting attendance, meeting summaries, disconnecting the integration, troubleshooting, and FAQ.
11 | 404 — Branded Error Page | https://fasttrackr.ai/404 | pages/404.md | ✅ Complete | Branded 404 'Page Not Found' page. Includes suggested headline, body copy, and CTAs (Home, Features, Contact, Try for Free). Notes: must return HTTP 404 status; configure Cloudflare for all unmatched routes.
12 | FPA Landing Page | https://fasttrackr.ai/fpa | → Redirect to /contact | 🔀 Redirect | Page redirects to /contact. No MD file needed. Configure a 301 redirect from /fpa to /contact on the new Cloudflare server.
13 | Aon Landing Page | https://fasttrackr.ai/aon | → Redirect to /contact | 🔀 Redirect | Page redirects to /contact. No MD file needed. Configure a 301 redirect from /aon to /contact on the new Cloudflare server.
14 | OnePage CRM Landing Page | https://fasttrackr.ai/onepagecrm | → Redirect to /contact | 🔀 Redirect | Page redirects to /contact. No MD file needed. Configure a 301 redirect from /onepagecrm to /contact on the new Cloudflare server.
15 | Resources for Financial Advisors | https://fasttrackr.ai/resources-for-financial-advisors | pages/resources-for-financial-advisors.md | ✅ Complete | Comprehensive resource hub for financial advisors and RIAs. Categorised articles on AI in client communication, document processing, client prospecting, compliance, wealth management strategy, advisor trends, and FastTrackr AI in action. Key SEO content hub page.

## Summary
Migration Summary — fasttrackr.ai → Cloudflare
Total Pages Inventoried | 15
✅ MD Files — Complete & Ready | 12
🔀 Redirect to /contact (no MD file) | 3
Excluded from Migration (New Pages)
/pricing | New pricing page will be built fresh
/blog | New blog/CMS setup planned
Redirects to Configure on Cloudflare
/fpa → /contact | 301 permanent redirect
/aon → /contact | 301 permanent redirect
/onepagecrm → /contact | 301 permanent redirect
Notes
All ✅ MD files are in the /pages folder in this workspace.
For the branded /404 page, ensure Cloudflare serves it with HTTP status 404 for all unmatched routes.